## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-1 | Setup project environment (JDK, IntelliJ, GitHub, MySQL). Verified configurations and initial Git setup. | MUST HAVE | None | Sundhara Rameshwar.S | 3- Completed
Sprint 1 | Sprint 1 | US-2 | Implement Product model & InventoryManager with OOP + Exception Handling.Downloaded the MySQL Workbench for storing the data. | MUST HAVE | US-1 | Sundhara Rameshwar.S | 3- Completed
Sprint 1 | Sprint 1 | US-3 | Implement persistence layer using CSV for initial data handling and backup. | MUST HAVE | US-2 | Sundhara Rameshwar.S | 3- Completed
Sprint 1 | Sprint 1 | US-4 | Establish JDBC connection and verify SQL CRUD operations via MySQL Workbench. | MUST HAVE | US-3 | Sundhara Rameshwar.S | 3- Completed
Sprint 1 | Sprint 1 | US-5 | Implement ProductDAO and DAOImpl interfaces with CRUD logic. | MUST HAVE | US-4 | Sundhara Rameshwar.S | 3- Completed
Sprint 1 | Sprint 1 | US-6 | Integrate JDBC CRUD methods with console UI to perform interactive operations using JDBC connectivity | MUST HAVE | US-5 | Sundhara Rameshwar.S | 3- Completed
Sprint 2 | Sprint 2 | US-7 | Implement Read (GetAll, GetByID) & Console Integration for admin operations. | MUST HAVE | US-6 | Sundhara Rameshwar.S | 3- Completed
Sprint 2 | Sprint 2 | US-8 | Implement Update & Delete functionalities with validation. | MUST HAVE | US-7 | Sundhara Rameshwar.S | 3- Completed
Sprint 2 | Sprint 2 | US-9 | Integrate CRUD into console menu for full functional flow. | MUST HAVE | US-8 | Sundhara Rameshwar.S | 3- Completed
Sprint 2 | Sprint 2 | US-10 | Add input validation and detailed exception handling in CRUD operations. | MUST HAVE | US-9 | Sundhara Rameshwar.S | 3- Completed
Sprint 2 | Sprint 2 | US-11 | Implement JUnit tests for DAO and utility layers to validate data logic. | MUST HAVE | US-10 | Sundhara Rameshwar.S | 3- Completed
Sprint 2 | Sprint 2 | US-12 | Implement CSVHelper for data export & synchronization with MySQL. | MUST HAVE | US-11 | Sundhara Rameshwar.S | 3- Completed
Sprint 3 | Sprint 3 | US-13 | Develop EmailService to send reports and alerts using JavaMail API (SMTP). | MUST HAVE | US-12 | Sundhara Rameshwar.S | 3- Completed
Sprint 3 | Sprint 3 | US-14 | Integrate EmailService into the App’s admin menu for sending product reports. | MUST HAVE | US-13 | Sundhara Rameshwar.S | 3- Completed
Sprint 3 | Sprint 3 | US-15 | Integrate database, CSV, and email modules for unified reporting workflow | SHOULD HAVE | US-14 | Sundhara Rameshwar.S | 3- Completed
Sprint 3 | Sprint 3 | US-16 | Implement OTP service for email verification during user registration. | COULD HAVE | US-13 | Sundhara Rameshwar.S | 3- Completed
Sprint 3 | Sprint 3 | US-17 | Add “Verify Email” and “Resend OTP” functions in registration menu. | MUST HAVE | US-16 | Sundhara Rameshwar.S | 3- Completed
Sprint 3 | Sprint 3 | US-18 | Enhance user registration/login flow with OTP validation and secure hashing. | MUST HAVE | US-16 | Sundhara Rameshwar.S | 3- Completed
Sprint 4 | Sprint 4 | US-19 | Implement Stock Alert Service to monitor threshold-based low stock alerts. | MUST HAVE | US-18 | Sundhara Rameshwar.S | 3- Completed
Sprint 4 | Sprint 4 | US-20 | Develop scheduled alert generator for recurring stock monitoring. | MUST HAVE | US-19 | Sundhara Rameshwar.S | 3- Completed
Sprint 4 | Sprint 4 | US-21 | Integrate email notifications for stock alerts in the main menu. | MUST HAVE | US-19 | Sundhara Rameshwar.S | 3- Completed
Sprint 4 | Sprint 4 | US-22 | Add search functionality by name, category, and ID for admin/user roles. | MUST HAVE | US-9 | Sundhara Rameshwar.S | 3- Completed
Sprint 4 | Sprint 4 | US-23 | Conduct full end-to-end testing of registration, OTP, email, and alerts. | MUST HAVE | US-18 | Sundhara Rameshwar.S | 3- Completed
Sprint 4 | Sprint 4 | US-24 | Package, finalize, and deploy the full Inventory Management System build. | MUST HAVE | US-23 | Sundhara Rameshwar.S | 3- Completed
Note on F1: ====== ID#AAABqnR-1bo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.